## Slide 1: Week 7: PM Review
G3T3
Darren Tay
Shu Wen
Jeremy Ong
Nabilah Banu
Zhi Hui

## Slide 2
Functionalities
Project Schedule
Roles & Responsibilities
Metrics
PP Team & Rotation Plans
T3
Required Functionalities:
Login
Bootstrap
Basic App Usage Report
Top-k App Usage Report
Smartphone Overuse Report
Dual interfaces
Loading location data
Deletion of data
Smartphone Usage Heatmap
Social Activeness Report
No Add/ Drop

## Slide 3
Functionalities
Project Schedule
Roles & Responsibilities
Metrics
PP Team & Rotation Plans
Bird-eye view of project
ITERATION 1
28/8/2015 12/9/2015
ITERATION 2
12/9/2015
25/09/201
ITERATION 3
25/09/2015
09/10/2015
Project Planning
Sequence Diagram
Use Case Diagram
ER Diagram
Delete Location
Login/Logout
Basic App Report
Usage Heatmap
Sequence Diagram
Bootstrap
Class Diagram
Sequence Diagram

## Slide 4
Functionalities
Project Schedule
Roles & Responsibilities
Metrics
PP Team & Rotation Plans
Bird-eye view of project
ITERATION 4
09/10/2015
23/10/2015
ITERATION 5
23/10/2015
05/11/2015
ITERATION 6
05/11/2015
End
Overuse Report
Top –K Report
Social Activeness
Deploy to OpenShift
Seek loopholes
Final Presentation
Submission
Test new ‘Test Cases’
Buffer
Debugging

## Slide 5
Functionalities
Project Schedule
Roles & Responsibilities
Metrics
PP Team & Rotation Plans
Buffer time
Iteration 5: 1st half of the Iteration 23/10/2015 - 30/11/2015
1
2
3
4
5
6

## Slide 6
Functionalities
Project Schedule
Roles & Responsibilities
Metrics
PP Team & Rotation Plans
Milestones
Week 11[Iteration 5] : Application ready for UAT
Week 5 [Iteration 2] : Start Coding
Week 7 [Iteration 3]: Technical Documents completed
Week 13 [Iteration 6] : Project Submission

## Slide 7
Functionalities
Project Schedule
Roles & Responsibilities
Metrics
PP Team & Rotation Plans
Critical Path ---------

## Slide 8
Functionalities
Project Schedule
Roles & Responsibilities
Metrics
PP Team & Rotation Plans
Cont.
---------

## Slide 9
Functionalities
Project Schedule
Roles & Responsibilities
Metrics
PP Team & Rotation Plans
Task Metrics
Bug Metrics
Time-Boxing
0%
Burndown Chart
IMPACT | 
Low 1Point | Not important. [typo, alignment etc.]
High 5 Points | System runs but some functions not working. Fix during planned debugging
Critical 10 Points | System down. Fix before continue
Score = 1 x num(low)
+ 5 x num(high)
+10 x num(critical)
[Actual task/ estimated task]
Notes: Current value for each metrics
any action based on mitigation plan
https://docs.google.com/spreadsheets/d/1Sp80UyYZO_gT89sFfwVYJIofxsbHAiiVybEl8Qu1xrA/edit#gid=0

## Slide 10
Functionalities
Project Schedule
Roles & Responsibilities
Metrics
PP Team & Rotation Plans
Notes: Rotation plan
wgich pm which milestone

## Slide 11
Who is Doing What
ITERATION 1
PM: Jeremy
  Use Case Diagram
  Domain Diagram
Pair 1: Darren + Shu Wen
  ER Diagram
Pair 2: Zhi Hui + Nabilah
  Sequence Diagram

## Slide 12
Who is Doing What
ITERATION 2
PM: Zhi Hui
  Supervisor Meeting 1 Slides
  Task metrics & Test plan
Pair 1: Darren + Nabilah
  Bootstrap
Pair 2: Jeremy + Shu Wen
  Sequence Diagrams
  Class diagram
  Test cases: Bootstrap
  Test files

## Slide 13
Who is Doing What
ITERATION 3
PM: Nabilah
  PM Review Slides
  Prepare Test Cases
  Regression Testing
Pair 1: Darren + Shu Wen
  Bootstrap (Cont.)
  Basic App Report
  Deploy to Openshift
Pair 2: Jeremy + Zhi Hui
  Login Logout
  Delete Location
  Usage Heatmap

## Slide 14
Who is Doing What
ITERATION 4
PM: Darren
  Supervisor Meeting 2 Slides
  Update diagrams
  Deploy to Openshift
  Regression Testing
Pair 1: Jeremy + Zhi Hui
  Social Activeness Report
Pair 2: Nabilah + Shu Wen
  Top-K Report
  Overuse Report

## Slide 15
Who is Doing What
ITERATION 5
PM: Shu Wen
  Supervisor Meeting 2 Slides
  Prepare for UAT
Pair 1: Jeremy + Nabilah + Pair 2: Darren + Zhi Hui
Testing of possible new Test Cases for the Overall System
-in preparation of UAT

## Slide 16
Who is Doing What
ITERATION 6
PM: Jeremy
  Match final submission with requirements
  Final presentation slides
  Deploy application to OpenShift
Pair 1: Darren + Zhi Hui
  Thorough debugging
Pair 2: Shu Wen + Nabilah
  Seek loopholes in test cases
  Buff up test cases to look for new bugs

## Slide 17
Functionalities
Project Schedule
Roles & Responsibilities
Metrics
PP Team & Rotation Plans
Notes: Rotation plan
wgich pm which milestone

## Slide 18
End of Presentation
Q & A

## Slide 19: Appendix : full critical path

## Slide 20: Appendix

## Slide 21: Appendix
 | Iteration 1: 28/8/2015 - 12/9/2015 (Weeks 2 + 3) | Iteration 2: 12/09/2015 - 25/09/2015 (Weeks 4 & 5) | Iteration 3: 25/09/2015 - 09/10/2015 (Weeks 6 + 7) | Iteration 4: 09/10/2015 - 23/10/2015 (Weeks 8 + 9) | Iteration 5: 28/10/2015 - 05/11/2015 (Weeks 10 + 11) | Iteration 6: 06/11/2015 - 20/11/2015 (Weeks 12 + 13)
PM | Jeremy | Zhi Hui | Nabilah | Darren | Shuwen | Jeremy
Pair 1 | Darren Shu Wen | Darren Nabilah | Darren Shu Wen | Jeremy Zhi Hui | Jeremy Nabilah | Darren Zhi Hui
Pair 2 | Zhi Hui Nabilah | Jeremy Shuwen | Jeremy Zhi Hui | Shu Wen Nabilah | Darren Zhi Hui | Shu Wen Nabilah