## TestPlan
TEST Plan
Who are responsible for it? | PM of the iteration
When to do it? Frequency etc | Every Thursday after functions completed
Test Setup (People / Computers etc) | PM with own laptop
When to fix bugs? | Friday and over the weekends
Fix the bugs in pairs | Yes

## Bootstrap
TEST CASES | [5 empty] | Testing |  | Regression Testing |  | Regression Testing(Iteration5)
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail | Actual Results | Pass/Fail | Actual Result
1 | BootStrap | Validate that zip file with the correct file names,file type, number of files, input can be bootstrapped successfully. | File: bs-test-1.zip | Put the zip file into input field. Submit. | Bootstrap success. All bootstrap details are correctly displayed in the database. | Values printed as expected | Pass | Values printed as expected | Pass | Values printed as expected | Pass
2 | BootStrap | Error messages from validation in demographics.csv (based on mac-address,password,email,gender) are returned to admin correctly. | File: bs-test-2.zip | Put the zip file into input field. Submit. | Bootstrap success. However, 8 error messages are returned to admin. Row 3,4 will consist of mac-address error. Row 5,6,7 will consist of password error. Row 8,9 will consist of email error. Row 10 will consist of gender error. Rows 3,4,5,6,7,8,9,10 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass | Values printed as expected | Pass | Returns -1 for all blocks | Fail
3 | BootStrap | Error messages from validation in app-lookup.csv (based on app-id,app-category) are returned to admin correctly. | File: bs-test-3.zip | Put the zip file into input field. Submit. | Bootstrap success. However, 3 error messages are returned to admin. Row 3 ,5 will consist of app-id error. Row 10 will consist of app-category error. Rows 3,5,10 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass | Values printed as expected | Pass | Values printed as expected | Pass
4 | BootStrap | Error messages from validation in apps.csv (based on app-id,mac-address,timestamp) are returned to admin correctly. | File: bs-test-4.zip | Put the zip file into input field. Submit. | Bootstrap success. However, 6 error messages are returned to admin. Row 1,2 will consist of mac-address "invalid mac address" error. Row 3 will consist of mac-address "no matching mac address" error. Row 5 will consist of app-id error. Row 7 will consist of incorrect timestamp error. Row 10 will consist of a duplicated of row 9. Rows 1,2,3,5,7,9 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass | Values printed as expected | Pass | Row 7 did not return a timestamp error | Fail
5 | BootStrap | Error messages from validation in location.csv (based on mac-address,location-id, timestamp) are returned to admin correctly. | File: bs-test-5.zip | Put the zip file into input field. Submit. | Bootstrap success. However, 6 error messages are returned to admin. Row 1 will consist of invalid location-id error. Row 5,6,20 will consist of invalid mac address error. Row 7 will consist of invalid timestamp error. Row 9 will consist of a duplicate of row 8. Rows 1,5,6,7,9,20 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass | Values printed as expected | Pass | Only return 1 error message | Fail
6 | BootStrap | Error messages from validation in location-lookup.csv (based on location-id,semantic-place) are returned to admin correctly. | File: bs-test-6.zip | Put the zip file into input field. Submit. | Bootstrap success. However, 5 error messages are returned to admin. Row 1,2 will consist of invalid location id error. Row 8,9,10 will consist of invalid semantic place error. Rows 1,2,8,9,10 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass | Values printed as expected | Pass | It shows no error with records | Fail

## AddBatch
[6 empty] | Testing |  | Regression Testing |  | Regression Testing (Iteration5)
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail | Actual Results | Pass/Fail | Actual Results | Pass/Fail
1 | AddBatch | All files except demographics.csv should be throwing error messages for duplicates | File: ab-test-1.zip | Put the zip file into input field. Submit. | AddBatch success. However, error messages for app.csv and location.csv should be returned as all are duplicates. | Values printed as expected | Pass | Values printed as expected | Pass | Returned no matching mac address,invalid app instead of duplicates | Fail
2 | AddBatch | Error messages from validation in demographics.csv (based on mac-address,password,email,gender) are returned to admin correctly. | File: ab-test-2.zip | Put the zip file into input field. Submit. | AddBatch success. However, 8 error messages are returned to admin. Row 3,4 will consist of mac-address error. Row 5,6,7 will consist of password error. Row 8,9 will consist of email error. Row 10 will consist of gender error. Rows 3,4,5,6,7,8,9,10 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass | Values printed as expected | Pass | Wrong error messages for different rows | Fail
3 | AddBatch | Error messages from validation in app.csv (based on app-id,mac-address,timestamp) are returned to admin correctly. | File: ab-test-3.zip | Put the zip file into input field. Submit. | AddBatch success. However, 18 error messages are returned to admin. Rows 3, 4, 5 have invalid timestamp, Rows 3, 5, 9, 11, 15 have duplicate mac address, Row 14 has invalid appid, Row 16 has no matching appid, | Values printed as expected | Pass | Values printed as expected | Pass | Wrong error messages for different rows | Fail
4 | AddBatch | Error messages from validation in location.csv (based on mac-address,location-id, timestamp) are returned to admin correctly. | File ab-test-4.zip | Put the zip file into input field. Submit. | Addbatch Success. Rows 2, 5, 7, 22, 26 have invalid timestamp. Rows 5, 10, 16, 22, 27, 28 have invalid location. Rows 5, 11, 21, 24 and 25 as well as 29 and 31. Rows 13, 24, 28 and 32 have duplicate mac addresses, but not duplicate timestamp. Rows 3, 4, 8, 12, 17, 19, 20 and 30 are duplicates in the database while rows 6, 9, 13, 14, 15, 18, 23, 25, 32. | Values printed as expected | Pass | Values printed as expected | Pass | Wrong error messages for different rows | Fail
5 | AddBatch | No error messages should be thrown. All files have unique records except for demographics.csv (assumed unique) | File ab-test-5.zip | Put the zip file into input field. Submit. | Addbatch success, no error messages. | Values printed as expected | Pass | Values printed as expected | Pass | Crashes with nullpointer exception | Fail

## Login
TEST CASES | [5 empty] | Testing |  | Regression Testing
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail | Actual Results | Pass/Fail
1 | User Login | Validate that correct username and password allow successful login | email:sean.tan.2011 (email part before the @ sign) password: asdf0000 from demographics.csv | Enter email ID and password, click login | A homepage with all the functions a User can access | This is home page for student users! | Pass | This is home page for student users! | Pass
2 | User Login | User enter email address instead of email ID | email: abcabc password: zxklfjds from demographics.csv | Enter user's full email address with the correct password and click login | Error Message saying invalid username/password on the log in page. | invalid username/password | Pass | invalid username/password | Pass
3 | User Login | User enter invalid email Id | email: abcabc password: zxklfjds from demographics.csv | Enter invalid email id with any password found in demographics.csv and click login | Error Message saying invalid username/password on the log in page. | invalid username/password | Pass | invalid username/password | Pass
4 | User Login | User enter invalid password | email: admin password: zxklfjds from demographics.csv | Enter valid email id with wrong password and click login | Error Message saying invalid username/password on the log in page. | invalid username/password | Pass | invalid username/password | Pass
5 | User Login | User clicks login without entering any email id or password |  | Just click on login button | Error Message saying field should not be empty | error msg:" pls fill out this fied | Pass | error msg:" pls fill out this fied | Pass
6 | User Login | User only enter emailId | email:admin password: from demographics.csv | Enter a valid email id and click login | Error Message saying field should not be empty | error msg:" pls fill out this fied on username field | Pass | error msg:" pls fill out this fied on username field | Pass
7 | User Login | User only enter password | email: password:123 from demographics.csv | Enter only a valid password and click login | Error Message saying field should not be empty | error msg:" pls fill out this fied on password field | Pass | error msg:" pls fill out this fied on password field | Pass
8 | Admin Login | Validate that correct admin username and password allow successful login | email:admin password:123 from admin login.csv | Enter username and password, click login | A homepage with all the functions an admin can access | This is home page for admin! | Pass | This is home page for admin! | Pass
9 | Admin Login | admin does not enter username and password | email: password: from demographics.csv | Just click login | Error Message saying field should not be empty | error msg:" pls fill out this fied | Pass | error msg:" pls fill out this fied | Pass
10 | Admin Login | Admin only enter password | email: password:123 from admin login.csv | Enter the password and click login | Error Message saying field should not be empty | error msg:" pls fill out this fied | Pass | error msg:" pls fill out this fied | Pass
11 | Admin Login | Admin only enter username | email: admin password: from admin login.csv | Enter the username and click login | Error Message saying field should not be empty | error msg:" pls fill out this fied | Pass | error msg:" pls fill out this fied | Pass
12 | Admin Login | Admin enter wrong username | email: abcabc password: <password> from admin Login.csv | Enter the invalid username with password given and click login | Error Message saying invalid username/password on the log in page. | invalid username/password | Pass | invalid username/password | Pass
13 | Admin Login | Admin enter wrong password | email: admin password: abcabc from admin Login.csv | Enter the invalid password with username given and click login | Error Message saying invalid username/password on the log in page. | invalid username/password | Pass | invalid username/password | Pass
14 | User Login | correct username and password but password in Caps on | email:admin2 (email part before the @ sign) password: admin123 from demographics.csv | Enter valid emailID and valid password but the password in Capital Letters | Error Message saying invalid username/password on the log in page. | unable to check as given password is numerical. | Fail | This is home page for student users! | Pass

## DeleteLocation
TEST CASES | [5 empty] | Regression Testing(Iteration 5)
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | upload the csv file and delete from location-delete.csv | Loop through the records in the csv and delete them from location.csv if they exist in the location.csv | location-delete.csv | at the delete data page, upload location-delete.csv | message: 16 location fies deleted .shown on the delete homepage
2 | upload the csv file and delete from location-delete.csv | Loop through the records in the csv and delete them from location.csv if they exist in the location.csv | location-delete_mixture.csv | at the delete data page, upload location-delete_mixture.csv | Message: 16 files deletd and 5 records not found. shown on the delete homepage
|  | admin will enter mac address, start date and end date. And the records that matches the input will be deleted | location-delete.csv

## Overuse
Test Cases **(FOR THESE TESTS, PLEASE USE sean.tan.2011@business.smu.edu.sg, asdf0000) | [7 empty] | Side Note: Time needs to be removed for test cases to pass
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Regression Testing | Pass/Fail | Need to update with time
1 | Smartphone Overuse | check for blank fields | no input | just click submit | Please fill out this fields | Please fill out this fields | Pass
2 | Smartphone Overuse | invalid timestamp | start date : 06/04/0000 end date: 06/04/0000 | Input: start date : 06/04/0000 end date: 06/04/0000 | Value must be 01/01/1970 or later | Value must be 01/01/1970 or later | Pass
3 | Smartphone Overuse | End date before start date and vice versa | start date : 07/04/2015 end date: 06/04/2015 | Input: start date : 07/04/2015 end date: 06/04/2015 | End date should be after Start date | Overuse results: Normal Usage results: Light,0 Gaming: Light,0 Access: Light ,0 | Fail
4 | Smartphone Overuse | correct result shown | start date : 06/04/2015 end date: 06/04/2015 | Using bs-test-1, enter inputs start date : 06/04/2015 end date: 06/04/2015 | Overall: Normal Smartphone: Light Gaming: Light Access: Light | Overall: Normal Smartphone: Light,0 Gaming: Light,0 Access: Light,0 | Pass
5 | Smartphone Overuse | Checks for overuse Checks whether the functions returns as an overuse (1 day) Tests if it is indeed calculations that 120s returns 120s and 121s returns 10s First to handle more than one static timing User starts to shift app (Meaning not just 1 static app) | start date : 06/04/2015 end date: 06/04/2015 | Using overuse-test-1 to bootstrap, enter inputs start date : 06/04/2015 end date: 06/04/2015 | Overall: Overuse Smartphone: Severe Gaming: Moderate Access: Light | Overuse results: Overusing Usage results: Light,5 Gaming: Moderate,1 Access: Severe,37056 | Fail | Overuse results: Overusing Usage results: Severe 23312 Gaming Usage results: Moderate 3944 Access Frequency results: Light 0.96 | Fail
6 | Smartphone Overuse | Checks for overuse Checks whether the functions returns as an overuse (4 days) Tests if can handle over more than 1 day. Gaming will vary across the 4 days, along the borderline. User doesn't use the same app in chunks | start date : 06/04/2015 end date: 09/04/2015 | Using overuse-test-2 to bootstrap, enter inputs start date : 06/04/2015 end date: 09/04/2015 | Overall: Overuse Smartphone: Light Gaming: Severe Access: Light | Overuse results: Overusing Usage results: Light,2 Gaming: Severe,11 Access: Severe,7140 | Fail | Overuse results: Overusing Usage results: Moderate 13133 Gaming Usage results: Severe 10851 Access Frequency results: Light 0.66 | Fail
7 | Smartphone Overuse | Checks for overuse Checks whether the functions returns as an overuse (3 days) Tests if gaming can separate between 3 appids and get moderate. Across more than 1 day, access will be close to the borderline | start date : 06/04/2015 end date: 08/04/2015 | Using overuse-test-3 to bootstrap, enter inputs start date : 06/04/2015 end date: 08/04/2015 | Overall: Overuse Smartphone: Light Gaming: Moderate Access: Severe | Blank screen | Fail | Overuse results: Overusing Usage results: Severe 18190 Gaming Usage results: Severe 15566 Access Frequency results: Light 1.25
8 | Smartphone Overuse | Checks for overuse Checks whether the functions returns as an overuse (1 day) Overloads hours for access, tests whether can give the same result for all severe Tests whether it takes each hour into account | start date : 06/04/2015 end date: 06/04/2015 | Using overuse-test-4 to bootstrap, enter inputs start date : 06/04/2015 end date: 06/04/2015 | Overall: Overuse Smartphone: Severe Gaming: Severe Access: Severe | Overuse results: Overusing Usage results: Light,1 Gaming: Severe,4 Access: Severe,12432 | Fail | Overuse results: Overusing Usage results: Severe 31382 Gaming Usage results: Severe 19645 Access Frequency results: Light 1.38

## Heatmap
TEST CASES | [5 empty] | Iteration 3 -Regression Testing
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | check for blank fields | no input | just click submit |  | error msg: please fill in all the fields
2 | valid start and end time | start time and end time in the right format | bootstrap data v1, enter 6/4/2015 for start, 13:14:00 for time, floor B1, | enter start and and time, and B1 for floor and click submit | SMUSISB1CORRIDORTOLKS,5,21 and more SMUSISB1CORRIDORTOSOE,4,14 to 20 SMUSISB1LIFTLOBBY,5,21 and more SMUSISB1NEAROSL,5,21 and more SMUSISB1STUDYAREA,5, 21 and more