## Mitigation Metrics
Score(%) | Action
TM <= 50 | 1.Immediately, inform your supervisor about the slip within 24 hours.
2.Then use the same mitigation as the category 50 < TM <= 90 and seriously consider dropping tasks.
50 < TM <= 90 | 1.Re-estimate the tasks for the future iterations.
2.Deduct the number of days behind schedule from buffer days.
3.If there is no more buffer day, decide the functionalities to drop.
90 < TM <= 110 | Our estimates are fairly accurate, and we are roughly on track.
1.Add/Deduct the number of days behind schedule from buffer days.
2.If there is no more buffer day, decide the functionalities to drop
110 < TM <= 150 | Gross over-estimated the effort required.
1.Re-estimate the tasks for the future iterations.
2.Add the number of days gained to buffer days.
150 < TM | 1.Immediately, inform your supervisor about the slip within 24 hours.
2.Then use the same mitigation as the category 110 < TM <= 150

## Iteration 1
Task | Score
Draw domain diagram | 1
Come out with project schedule | 1
Draw use case diagram | 1
Draw SD for initial bootstrap | 1
Draw ER Diagram | 1
Conduct per sharing | 1
PM Handover | 1
Update next Iteration schedule | 1
Total Task Done | 8
Total number of Task | 8
Task Score | 100
Mitigation Plan | Go ahead with planned schedule without any changes to buffer timing.

## Iteration 2
Task | Score
Update Bootstrap SD | 1
Draw SD Basic App Usage Report | 1
Draw SD Bootstrap Location Data | 1
Draw SD Deleting Location Data | 1
Draw SD Smartphone Overuse Report | 1
Draw SD Top-K Report | 1
Task Metrics | 1
Test Plan | 1
Prepare supervisor meeting slides | 1
Update SDs | 1
Bootstrap Logic | 0
Bootstrap JSON | 0
Bootstrap UI | 0
Deploy to openshift | 0
Test Bootstrap | 0
Conduct Peer Sharing Session | 1
Internal meeting w/ PM Handover | 1
Update next Iteration schedule | 1
Supervisor meeting | 1
Internal meeting 1 | 1
Total Task Done | 15
Total number of Task | 20
Task Score | 75
Mitigation Plan | Bootstrap function pushed over to iterartion 3

## Iteration 3
Task | Score
Slides for PM Review | 1
Update SDs | 1
Bootstrap UI | 1
Bootstrap Logic | 1
Bootstrap JSON | 1
Prepare Testcase for delete data function | 1
Consolidate Class Diagrams | 1
Consolidate ER Diagrams | 1
Draw SD for login | 1
Draw SD for Smartphone Usage Heatmap | 1
Prepare Testcase for basic app usage | 1
Prepare testcase for CRUD Location data | 1
Prepare testcase for smartphone usage heatmap | 1
Prepare testcase for login | 1
Login Logic | 1
Login UI | 1
Login JSON | 1
Delete Location UI | 1
Delete Location Logic | 1
Delete Location JSON | 1
Test Basic App Usage | 0
Test Delete Location | 0
Test Login | 1
SmartPhone Usage Heatmap UI | 1
SmartPhone Usage Heatmap Logic | 1
SmartPhone Usage Heatmap JSON | 1
PM Review | 1
Basic App Report Logic | 0
Basic App Report JSON | 0
Basic App Report UI | 0
Test Bootstrap | 1
Debug Heatmap | 1
Debug Login | 1
Debug Delete Location | 0
Debug Bootstrap | 0
Integrate functions | 1
Deploy to OpenShift | 1
Debug after deployment | 1
Regression Testing | 1
Peer Sharing | 1
PM Handover | 1
Internal meeting | 1
Update next Iteration | 1
Total Task Done | 36
Total number of Task | 43
Task Score | 83.7209
Mitigation Plan | 1) basic app (logic,UI,JSON,Testing) 2)Test & Debug Delete Location 3)Debug Bootstrap Pass all this to Next Iter

## Iteration 4
Task | Score
Test Basic App Usage (Openshift) | 1
Test Delete Location (Openshift) | 1
Basic App Report Function1 | 1
Basic App Report Function2 | 1
Basic App Report Function3 | 1
Debug Delete Location (Openshift) | 1
Debug Bootstrap (Openshift) | 1
Preparation of Material for supervisor Meeting | 1
Preparation of slides for Supervisor Meeting (Week 9) | 1
Update Bug Metrics | 1
Bootstrap Diagram | 1
Building of Test Cases Top-K | 1
Building of Test Cases (Smartphone Overuse Report) | 1
Building of Test Cases (Social Activeness) | 1
Building of Test Cases (Basic App) | 1
Develop Top-K students Most Apps usage (App Cat) | 1
Develop Top-K schools Most Apps usage (App Cat) | 1
Update Diagrams | 1
Social Activeness Report Logic | 0 | SW
Social Activeness Report UI | 0 | SW
Social Activeness Report JSON | 0 | SW
Friday Meeting | 1
Friday Meeting (PM handover) | 1
Pre-Supervisor Meeting | 1
Supervisor Meeting | 1
Smartphone overuse report Logic | 1
Smartphone overuse report UI | 1
Smartphone overuse report JSON | 1
Test TOP-K | 0
Test Basic App Usage | 1
Test Smartphone Overuse Report | 1
Debug Top-K | 0
Debug Basic App Usage | 1
Debug Smartphone Overuse Report | 1
Deploy application to OpenShift (Overuse + Basic App) | 1
Deploy application to OpenShift (Top-K) | 1
Testing on OpenShift (Overuse) | 1
Testing on OpenShift (Basic App) | 1
Debugging Overuse | 0 | SW
Debugging Basic App | 0 | SW
Total Task Done | 33
Total number of Task | 40
Task Score | 82.5
Mitigation Plan

## Iteration 5
Task | Score
Building of additional Test Case for Top k | 1
Testing of Top k report | 1
Debugging of Top-K report | 1
Preparation of slides for Supervisor Meeting 3 | 1
Changes to Bootstrap (Location-Delete) (Additional Change in Requirement) | 1
Supervisor Meeting 3 | 1
Building New Test Cases for Bootstrap change of demographic field (Additional Change in Requirement) | 1
Building Test Cases for Social Activeness Function | 1
Building of new Test Cases for Basic Add based on (Additional Change in Rerquiremenr | 1
Changes to Bootstrap - Additional Demographics (CCA) (Additional Change in Requirement) | 1
Debugging of Heatmap | 1
Debugging of Overuse | 1
Internal Meeting | 1
Testing of Bootstrap - Delete Location Data (Additional Change in Requirement) | 1
SOCIAL ACTIVENESS FUNCTION | 1
Testing of Bootstrap additional Demographics (Additional Change in Requirement) | 1
Changes to Basic App Requirement (Additional Change in Requirement) | 1
Regressison Testing | 1
Debugging of Basic App- Based on New test Cases (Additional Change in Requirement) | 1
Debugging of BootStrap Change in Demographics - Based on new Test Cases (Additional Change In Requirement) | 1
Debugging of BootStrap Delete Location - Based on new Test Cases (Additional Change In Requirement) | 1
Debugging of Social Activeness Report | 1
Deploy to OpenShift | 1
Overall Integration before deployment | 1
Testing of Bootstrap Basic App Function (Additional Change in Requirement) | 1
Testing of Social Activeness Function | 1
Update Metric and Apply Mitigration | 1
Revise Diagrams | 1
Code Sharing | 1
Internal Meeting | 1
PM Handover (Knowledge transfer on schedule, metrics, admin etc) | 1
Update next iteration schedule | 1
User Acceptance Test | 1
Total Task Done | 33
Total number of Task | 33
Task Score | 100
Mitigation Plan

## Iteration 6
Task | Score
Update and finalise ACTIVENESS SD | 1
Update and finalise BASIC APP SD | 1
Update and finalise Class Diagram | 1
Update and finalise HEATMAP SD | 1
Update and finalise Logical Diagram | 1
Update and finalise OVERUSE SD | 1
AddBatch DEBUGGING | 1
Basic App DEBUGGING | 1
Bootstrap DEBUG | 1
Bootstrap JAVADOC | 1
Final Presentation slides: Schedule, Metrics, Git usage, interesting experience | 1
Overuse DEBUGGING | 1
Topk DEBUGGING | 1
Topk JAVADOCS | 1
Update and finalise TOPK SDs | 1
Activeness DEBUGGING | 1
AddBatch JAVADOCS | 1
Heatmap DEBUGGING | 1
Overall UI DEBUGGING (fits requirements) | 1
Delete Location DEBUGGING | 1
Delete Location JAVADOCS | 1
Entity (inc. DAO) JAVADOCS | 1
Activeness JAVADOCS | 1
AddBatch SD | 1
Basic App JAVADOCS | 1
Bootstrap SD | 1
Delete Location SD | 1
Heatmap JAVADOCS | 1
Overuse JAVADOCS | 1
Update and finalise DELETE LOCATION SD | 1
Utility JAVADOCS | 1
Integration, with thorough debugging, bug bust until 0 bugs (bugs metric) as end goal | 1
Internal Meeting | 1
Regression Testing | 1
Deploy application to OpenShift | 1
Final Submission | 1
Total Task Done | 36
Total number of Task | 36
Task Score | 100
Mitigation Plan
Celebration