## Slide 1: Supervisor Review (week 9)
G3T3
Jeremy Ong
Darren Tay
Nabilah
Zhi hui
Shu Wen

## Slide 2: Meeting Agenda
Update on Functionalities
Milestones
How we will flown/fly
Iteration Schedule
Critical Path
Task Metrics
Bug Metrics
Sample Images of Project
Ideas we have utilized
Libraries used
Learning Experience
Where we will go from here

## Slide 3: Update on functionalities (Part 1)
T3
After Iter 3:
No Add/ Drop

## Slide 4: Update on Functionalities (Part 2)
Required Functionalities: | Status:
Login | Testing on Openshift Done
2. Bootstrap | JSON, Debugging
3. Basic App Usage Report | Function 1
4. Top-k App Usage Report | Undone
5. Smartphone Overuse Report | Undone
6. Dual interfaces | Constantly in work
7. Loading location data | JSON, Debugging
8. Deletion of data | JSON, Debugging
9. Smartphone Usage Heatmap | Testing on Openshift Done
10. Social Activeness Report | Undone

## Slide 5
Week 11[Iteration 5] : Application ready for UAT
Week 5 [Iteration 2] : Start Coding
Week 7 [Iteration 3]: Technical Documents completed
Week 13 [Iteration 6] : Project Submission
Milestones

## Slide 6
ITERATION 1
28/8/2015 12/9/2015
ITERATION 2
12/9/2015
25/09/2015
ITERATION 3
25/09/2015
09/10/2015
Project Planning
Sequence Diagram
Use Case Diagram
ER Diagram
Delete Location
Login/Logout
Basic App Report
Usage Heatmap
Sequence Diagram
Bootstrap
Class Diagram
Sequence Diagram
How we have flown
Notes: No white font

## Slide 7
ITERATION 4
09/10/2015
23/10/2015
ITERATION 5
23/10/2015
05/11/2015
ITERATION 6
05/11/2015
End
Basic App Report
Overuse Report
Top –K Report
Social Activeness
Deploy to OpenShift
Seek loopholes
Final Presentation
Submission
Test new ‘Test Cases’
Buffer
Debugging
How we Will fly

## Slide 8
Iteration Schedule
Current Iteration!
Notes: Rotation plan
wgich pm which milestone

## Slide 9: Iteration schedule (Current Part 1)
Iteration 4 PM: Darren
Pair 1:
Jeremy Ong
Tan Zhi Hui
Pair 2:
Yee Shu Wen
Nabilah

## Slide 10: Iteration Schedule (Current Part 2)
Pair 1:
Jeremy Ong
Tan Zhi Hui
Basic App Report (Week 1 of Iteration, 15/10 – 17/10)
Social Activeness (Week 2 of Iteration, 22/10 – 23/10)
Pair 2:
Yee Shu Wen
Nabilah
Smartphone overuse (Week 1 of Iteration, 12/10 – 13/10)
Top-K Report (Week 2 of Iteration, 17/10 – 23/10)

## Slide 11: Critical path (Iteration 1) 28/08 – 12/09 (16 Days)
Build Project Schedule
2 Days
Domain Diagram
1 Day
Use Case Diagram
1 Day
Sequence Diagram (Bootstrap)
3 Days
Buffer
1 Day
Entity-Relationship Diagram
2 Days
Buffer
1 Day
Consolidate Knowledge and Review Diagrams
1 Day
Critical Path
Non-Critical Path
Key:
Start
End

## Slide 12: Critical path (Iteration 2) 12/09 – 25/09 (15 Days)
Build Initial UI
1 Day
Sequence Diagram Smartphone Overuse
1 Day
Sequence Diagram Top-K
1 Day
Buffer
4 Days
Bootstrap
8 Days
Critical Path
Non-Critical Path
Key:
Start
End
Update Bootstrap Sequence Diagram
1 Day
Sequence Diagram for Basic App Report
1 Day
Sequence Diagram for Deletion Location Data
1 Day
Integrate Functionalities
1 Day
Consolidate Knowledge and Review Diagrams
1 Day

## Slide 13: Critical path (Iteration 3) 25/09 – 09/10 (15 Days)
Login/Logout
3 Days
Update and consolidate Class Diagram
2 Days
Sequence Diagram Login/Logout
1 Day
Critical Path
Non-Critical Path
Key:
Start
End
Consolidate all diagrams and check for matches.
Review Plans.
1 Day
Complete Bootstrap
6 Days
Sequence Diagram for Smartphone Usage
1 Day
Deploy to Openshift Login/Logout/Usage Heatmap
Integrating Functions
1 Day
Buffer
1 Day
Consolidate ER Diagram
1 Day
Bootstrap JSON
2 Days
Delete Location Data
2 Days
Smartphone Usage Heatmap
3 Days
Basic App Report
6 Days

## Slide 14: Critical path (Iteration 4) – Part 1 09/10 – 23/10 (15 Days)
Debugging Login/Logout/Usage Heatmap**
1 Day
Testing Bootstrap/Delete Location on Openshift
1 Days
Critical Path
Non-Critical Path
Key:
Start
Testing on Openshift
Login/Logout
Review Plans**
1 Day
Bootstrap JSON
1 Day
Top-K Report
5 Days
Deploy Bootstrap/Delete Location on Openshift
1 Day
Debugging Bootstrap/Delete Location
2 Days
Smartphone Overuse Report
3 Days
Social Activeness Report
3 Days
Basic App Report
3 Days
*Testing in Iter 4 as overran time in Iter 3
Buffer
4 Days
Integrating Functions
Deploy to Openshift (Basic App, Top-K, Social Active, Overuse)
1 Day
Debugging of Bootstrap/Delete Location
2 Day
Buffer
2 Days

## Slide 15: Critical path (Iteration 4)- Part 2 09/10 – 23/10 (15 Days)
Critical Path
Non-Critical Path
Key:
*Testing in Iter 4 as overran time in Iter 3
End
Debug Basic App
2 Days
Testing Basic App/Overuse
1 Day
Debug Overuse
1 Day
Buffer
1 Day
Buffer
1 Day
Integrating Functions
Deploy to Openshift (Basic App, Top-K, Social Active, Overuse)
1 Day

## Slide 16: Critical path (Iteration 5) 23/10 – 06/11 (15 Days)
Further Testing
1 Day
Buffer
1 Day
Debugging of Top-K
2 Days
Critical Path
Non-Critical Path
Key:
Start
End
Debugging of Activeness
1 Day
Testing of Activeness/Top-K
1 Day
Integrate Functionalities
Deploy to Openshift
1 Day
UAT Test
1 Day
Buffer
1 Day
Buffer
7 Days
Final Testing
2 Days
Final Diagram Update
2 Days

## Slide 17: Critical path (Iteration 6) 06/11 – 20/11 (15 Days)
Debugging on Openshift
1 Day
Critical Path
Non-Critical Path
Key:
Start
End
Final Deployment to Openshift
1 Day
Debugging (Post-UAT)
4 Days
Compilation of Report
2 Days
Presentation Preparation
7 Days

## Slide 18: Task metrics
Current:
7.14%
Time-Boxing
[Actual task/ estimated task]
    3 tasks/ 42 tasks
Previous:
83.3%
Time-Boxing
[Actual task/ estimated task]
    35 tasks/42 tasks

## Slide 19: Task metrics
Burndown chart and discussion:
  http://green.smu.edu.sg/pplog/metrics

## Slide 20: Task metrics
Burndown chart and discussion:
  http://green.smu.edu.sg/pplog/metrics

## Slide 21: Task metrics
Burndown chart and discussion:
  http://green.smu.edu.sg/pplog/metrics

## Slide 22: Task metrics
Burndown chart and discussion:
  http://green.smu.edu.sg/pplog/metrics

## Slide 23: Task metrics
Burndown chart and discussion:
  http://green.smu.edu.sg/pplog/metrics

## Slide 24: Bug Metrics
Bug Metrics
IMPACT | 
Low 1Point | Not important. [typo, alignment etc.]
High 5 Points | System runs but some functions not working. Fix during planned debugging
Critical 10 Points | System down. Fix before continue
Score = 1 x num(low)
+ 5 x num(high)
+10 x num(critical)
Current:
11
CRITICAL. Stop and Review.

## Slide 25: Bug Metrics
http://green.smu.edu.sg/is203/is203_g3t3/issues?assignee_id=&author_id=&label_name=&milestone_id=&scope=all&sort=created_desc&state=all

## Slide 26: Bug Metrics
Issue | Function | Severity | Raw Score | Final Score | Description | Closed
1 | Bootstrap | C | 10 | 0 | test | Y
2 | Heatmap | L | 1 | 0 | semanticplacein json output not sorted | Y
3 | Jsons | L | 1 | 0 | Jsons ordering unable to suit to wiki's requirements | Y
4 | Bootstrap | L | 1 | 1 | Bootstrap is unable to insert special characters | N
5 | UI - Links | H | 5 | 0 | Broken links | Y
6 | OpenShift-Bootstrap | H | 5 | 5 | appusage table and locationusage table not found; causes system to crash when initializing bootstrap. table name is caps Sensitive. need to rename in IDE. | N
7 | OpenShift-Heatmap | H | 5 | 0 | System crashes when heatmap request was sent. Possibly table name (appusage and locationusage) needs to be renamed (case sensitive) | Y
8 | Smartphone usage heatmap (via UI) | H | 5 | 0 | Crashes when input is: 6/04/2015 13:00:00 B1 | Y
9 | OpenShift-Initial Bootstrap | H | 5 | 5 | Bad Gateway:The proxy server received an invalid response from an upstream server. System unable to load a big zip file. (Might need to increase session time.) | N
Current Raw Score: 11!

## Slide 27: Sample Images of what we’ve done
*Note: Just some idea of the execution

## Slide 28: Sample Images of what we’ve done

## Slide 29: Sample Images of what we’ve done

## Slide 30: Ideas we have utilized – Login/logout
Response.sendRedirect to Protect Pages
Session variable to log individuals
Separate Entities for Admin/Student
Separate pages for Admin/Student (Different Functions)
Logout: Sendredirect + removeAttribute
Form Action: Type = Password

## Slide 31: Ideas we have utilized – Bootstrap
TreeMap:
  Unique keys for duplicates and passing variables
  Ties with JSON printing
  Easier to retrieve from Home page
Queries
  Checking with database for legit primary keys (appid, macadd, locationid)
  On Duplicate Update
  STR_TO_DATE
  Addbatch, Executebatch, Executequery (int[] return)

## Slide 32: Ideas we have utilized – Bootstrap
Zip File
  ZipInputStream, Part, ZipEntry, one-by-one retrieval.
  Ensures file input (UI side)
Servlet vs JSP
  Higher level implementation of return variables (1 Passing system)
  DoPost and DoGet (Difference)
Controllers (between JSON and Bootstrap UI)
Duplicate Checking at DAO level
Loading through DAOs

## Slide 33: Ideas we have utilized – Bootstrap (UI)
Form Action Type = File (To take in file inputs)
Checks for TreeMap. If null, don’t print anything except nothing passed.
Printing from TreeMap (if present) and sorting by rows

## Slide 34: Ideas we have utilized – Delete location
Add on to Bootstrap
For variables, follow Bootstrap, however, take in 3 variables (request.setAttributes)
Only returns if invalid variables OR success and rows deleted

## Slide 35: Ideas we have utilized – Usage Heatmap
Get location based on floor from locationDAO
Get unique users on the floor based on query by joining tables
Ensures no duplicates with groupby
Use LocationUsage entity to log
Ignores 5 minutes update

## Slide 36: Ideas we have utilized – Utility
Main checker whether methods work
  parseString, parseDate, parseInt (Checks for Null)
  Checkers (return Booleans)
    checkDate
    checkCategory/checkSchool
    checkEmail (validity)
    checkPassword

## Slide 37: Libraries We have used
Bootstrap: OpenCSV
JSON: GSON
UI: Bootstrap

## Slide 38: Learning experience
Bootstrap took much longer than expected
Usage Heatmap test cases still incomplete
Login fails two test casts
Latest not on Openshift
Foreseeable Problems for the future

## Slide 39
ITERATION 4
09/10/2015
23/10/2015
ITERATION 5
23/10/2015
05/11/2015
ITERATION 6
05/11/2015
End
Basic App Report
Overuse Report
Top –K Report
Social Activeness
Deploy to OpenShift
Seek loopholes
Final Presentation
Submission
Test new ‘Test Cases’
Buffer
Debugging
Where we will go from here

## Slide 40: THE END
Any questions?