## Metrics
Issue | Function | Severity | Raw Score | Final Score | Description | Closed | Severity
1 | Bootstrap - Main Function | C | 10 | 0 | test | Y | Low | L | 1
2 | Heatmap | L | 1 | 0 | semanticplace in json output not sorted | Y | High | H | 5
3 | JSONs | L | 1 | 0 | Jsons ordering unable to suit to wiki's requirements | Y | Critical | C | 10
4 | Bootstrap | L | 1 | 0 | Bootstrap is unable to insert special characters | Y
5 | UI - Links | H | 5 | 0 | Broken links | Y | Total impact score: | 36 | <--- PM NOTE!!!!
6 | OpenShift-Bootstrap | H | 5 | 0 | appusage table and locationusage table not found; causes system to crash when initializing bootstrap. table name is caps Sensitive. need to rename in IDE. | Y
7 | OpenShift-Heatmap | H | 5 | 0 | System crashes when heatmap request was sent. Possibly table name (appusage and locationusage) needs to be renamed (case sensitive) | Y
8 | Smartphone usage heatmap (via UI) | H | 5 | 0 | Crashes when input is: 6/04/2015 13:00:00 B1 | Y
9 | OpenShift-Initial Bootstrap | H | 5 | 5 | Bad Gateway:The proxy server received an invalid response from an upstream server. System unable to load a big zip file. (Might need to increase session time.) | N
10 | Openshift - Test case Fail | H | 5 | 0 | Error Messages for Location.csv and Location-Lookup don't tally | Y
11 | Openshift - Error messages not in sequence | L | 1 | 0 | The Error messages are not printed in the right order. Eg. Row 21 appears before row 10. | Y
12 | Bootstrap - Cannot load large data file (Data-zip 1) | C | 10 | 0 | The first data file of thousand entries cannot load finish before Java throws a Java Heap/Java out of memory error | Y
13 | Bootstrap - Cannot load large data file (Data-zip 3) | C | 10 | 0 | The third data file of a million entries cannot load finish before Java throws a Java Heap/Java out of memory error | Y
14 | Bootstrap - Duplicate entry rows are not returning | H | 5 | 0 | Duplicates in Bootstrap for the "most recent entry" have been solved, but then checking with the database for AddBatch are not displaying | Y
15 | Smartphone usage heatmap - misread instructions | C | 10 | 0 | Usage heatmap not supposed to take location data as "not there" after 5 minutes. | Y
16 | Bootstrap - Add Batch | H | 5 | 0 | Testing of Function | Y
17 | Bootstrap - JSON Token | H | 5 | 0 | Bootstrap JSON does not load. Token is not passing through properly. Always returns error | Y
18 | Login - Database | H | 5 | 0 | After logging out, database refreshes | Y
19 | Login - Values | C | 10 | 0 | After start-up, the program does not allow entry because values not in database | Y
20 | JSONs | L | 1 | 0 | Error Messages passing to the UI cannot be resused for the JSON. Therefore, the controller is not that helpful | Y
21 | Delete Location - UI | L | 1 | 0 | Delete Location UI not displaying properly | Y
22 | Delete Location | L | 1 | 0 | Delete Location Test | Y
23 | Delete Location - Logic | H | 5 | 0 | Delete Location (Choosing Options) don't delete the right choices | Y
24 | Bootstrap | H | 5 | 0 | Does not consider test case of no file uploaded | Y
25 | Delete Location - Values | H | 5 | 0 | Delete Location does not consider taking no values | Y
26 | Add Batch | H | 5 | 0 | Cannot read any number of files | Y
27 | Bootstrap | C | 10 | 0 | Fails Test case for App.csv | Y
28 | Bootstrap | C | 10 | 0 | Checking of date allows dates that have an inverted date format eg. DD/MM/YYYY instead of YYYY/MM/DD | Y
29 | Bootstrap | C | 10 | 0 | Categories are loaded in DAOs. Need to keep instantiating DAOs in reports. | Y
30 | Dates in UI | L | 1 | 0 | Dates should be in dd/mm/yyyy in the UI | Y
31 | Links on UI | L | 1 | 0 | Links should use relative path | Y
32 | JSON Tokens | C | 10 | 0 | JSON tokens not authenticating | Y
33 | Basic App Cat | H | 5 | 0 | When date '0000' is passed in, we pass back results of 0,0,0 instead of returning error | Y
34 | Basic App Dates | H | 5 | 0 | Basic app - start date can be after end date | Y
35 | Smartphone overuse | C | 10 | 0 | there is redundant 'start time' and 'end time' field in the UI | Y
36 | Smartphone overuse | L | 1 | 1 | fields do not go back to user chosen after generating report | N
37 | Top K Dates | H | 5 | 5 | Top-K does not take into account end date after start | N
38 | Top K Forced | H | 5 | 5 | Top-K does not take into account forced values | N
39 | Top-K Values | H | 5 | 5 | Top-K does not show the right values | N
40 | Top-K Printing | H | 5 | 5 | Top-K is not consistent in printing | N
41 | Top-K Dates | H | 5 | 5 | Top-K does not account for end date properly | N
42 | Top k Values | H | 5 | 5 | Top-k Does not account for the last record before midnight properly or there could be some logic issues | N

## Guidelines
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.