## Slide 1: Supervisor Meeting
G3T3
Tan Zhi Hui
Jeremy Ong
Shu Wen
Nabilah
Darren Tay

## Slide 2: Meeting Agenda
Progress
Goals for next iteration
Milestone
Problems
Respective roles & tasks
Metrics

## Slide 3: CYAN
Required Functionalities:
Login
Bootstrap
Basic App Usage Report
Top-k App Usage Report
Smartphone Overuse Report
Dual interfaces
Loading location data
Deletion of data
Smartphone Usage Heatmap
Social Activeness Report

## Slide 5: Progress
Iteration 1 – Planning & Design
Planning – setting of foundation
Use Case Diagram
ERD model
Domain Diagram
Bootstrap Sequence Diagram
Current Iteration
Revise of existing diagram
Set up Task Metric & PPlogs
Design remaining diagram
Class Diagram
Coding for bootstrap
Develop test cases and test file for bootstrap
Deploy and Test bootstrap functions

## Slide 6: Time Boxing
Project can be completed within the time
Keep to schedule
Sufficient buffer time
Notes: Do not want spill over to affect other functionalities

## Slide 7: Goals for next two weeks
Complete implementation of basic functionalities
  Bootstrap
  Login / logout
  CRUD
Standardise UI for admin and user platform

## Slide 8: Milestone
Finish the diagrams
Load function (Bootstrap) successful implemented
Functional for admin to upload
Notes: Finished preparation to delve into it

## Slide 9: Problems
Exiting
Not detailed enough for the diagram, coder might not be able to code [RESOLVED]
Potential
Team might be unfamiliar (JSON)
Wrong Estimation of time needed for Bootstrap functionality

## Slide 10: Risk Assessment
S/N | Risk Statement | Consequence | Likelihood | Impact | Level | Mitigation Strategy
1 | Team might be unfamiliar in coding in NetBeans and new language JSON | Delays in bootstrap function due to incorrect time estimates | High | High | A | Team to research and understand JSON Bootstrap Function will be given 1 and half iteration

## Slide 11: Roles and Tasks
Member(Role) | Iteration | Tasks
Jeremy Ong (PM) | 1 | Project schedule Use-Case diagram Domain Diagram Update next Iteration schedule PM handover
Jeremy Ong (Pair 2) | 2 | Sequence Diagram for Basic App Usage Report Sequence Diagram for Top-k app Usage Report Sequence Diagram for Smartphone overuse report Sequence diagram for deleting location data Prepare test case and test files for testing Class Diagram

## Slide 12: Roles and Tasks
Member(Role) | Iteration | Tasks
Tan Zhi Hui (Pair 2) | 1 | Bootstrap Sequence Diagram
Tan Zhi Hui (PM) | 2 | Preparation slides for supervisor meeting Task Metric Test Plan Update of Sequence diagram for bootstrap Update next Iteration schedule PM handover Testing of bootstrap

## Slide 13: Roles and Tasks
Member(Role) | Iteration | Tasks
Darren Tay (Pair 1) | 1 | ERD model
Darren Tay (Pair 1) | 2 | Sequence Diagram for Bootstrap Location Data Code Bootstrap UI, Logic and JSON Deploy to openShift Debugging (if any)

## Slide 14: Roles and Tasks
Member(Role) | Iteration | Tasks
Nabilah (Pair 2) | 1 | Bootstrap Sequence Diagram
Nabilah (Pair 1) | 2 | Sequence Diagram for Bootstrap Location Data Code Bootstrap UI, Logic and JSON Deploy to openshift Debugging (if any) Update Sequence Diagram for bootstrap

## Slide 15: Roles and Tasks
Member(Role) | Iteration | Tasks
Yee Shu Wen (Pair 1) | 1 | ERD model
Yee Shu Wen (Pair 2) | 2 | Sequence Diagram for Basic App Usage Report Sequence Diagram for Top-k app Usage Report Sequence Diagram for Smartphone overuse report Sequence diagram for deleting location data Prepare test case and test files for testing Class Diagram

## Slide 16: Task Metrics
Notes: https://docs.google.com/spreadsheets/d/1U8LG0BXlGYPczp9xnIFViaP86-Oerd2kIQKZnwwWPG4/edit#gid=544402806

## Slide 17: PPLogs
Notes: http://green.smu.edu.sg/pplog/

## Slide 18: Bug Metric
Notes: https://docs.google.com/spreadsheets/d/1Sp80UyYZO_gT89sFfwVYJIofxsbHAiiVybEl8Qu1xrA/edit#gid=0
Score should not be >= 10

## Slide 19: Critical Path
Implement Bootstrap
(4 days)
Design other Diagrams (5 days)
Implement
Login / Logout
(2 day)
Design Bootstrap diagram
(2 days)
Integrate functionalities
(2 days)
Implement CRUD Location
Data
(3 day)
Buffer
(1 day)
Notes: Critical path -
Time boxing, task based
If the task is brought to the next iteration, can the same pair finish coding for the function
If a task is brought to the next iteration, does it means that the rest might need to be adjusted