## Mitigation Metrics
Score(%) | Action
TM <= 50 | 1.Immediately, inform your supervisor about the slip within 24 hours.
2.Then use the same mitigation as the category 50 < TM <= 90 and seriously consider dropping tasks.
50 < TM <= 90 | 1.Re-estimate the tasks for the future iterations.
2.Deduct the number of days behind schedule from buffer days.
3.If there is no more buffer day, decide the functionalities to drop.
90 < TM <= 110 | Our estimates are fairly accurate, and we are roughly on track.
1.Add/Deduct the number of days behind schedule from buffer days.
2.If there is no more buffer day, decide the functionalities to drop
110 < TM <= 150 | Gross over-estimated the effort required.
1.Re-estimate the tasks for the future iterations.
2.Add the number of days gained to buffer days.
150 < TM | 1.Immediately, inform your supervisor about the slip within 24 hours.
2.Then use the same mitigation as the category 110 < TM <= 150

## Iteration 1
Task | Score
Draw domain diagram | 1
Come out with project schedule | 1
Draw use case diagram | 1
Draw SD for initial bootstrap | 1
Draw ER Diagram | 1
Conduct per sharing | 1
PM Handover | 1
Update next Iteration schedule | 1
Total Task Done | 8
Total number of Task | 8
Task Score | 100
Mitigation Plan | Go ahead with planned schedule without any changes to buffer timing.

## Iteration 2
Task | Score
Update Bootstrap SD | 1
Draw SD Basic App Usage Report | 1
Draw SD Bootstrap Location Data | 1
Draw SD Deleting Location Data | 1
Draw SD Smartphone Overuse Report | 1
Draw SD Top-K Report | 1
Task Metrics | 1
Test Plan | 1
Prepare supervisor meeting slides | 1
Update SDs | 1
Bootstrap Logic | 0
Bootstrap JSON | 0
Bootstrap UI | 0
Deploy to openshift | 0
Test Bootstrap | 0
Conduct Peer Sharing Session | 1
PM Handover | 1
Update next Iteration schedule | 1
Total Task Done | 13
Total number of Task | 18
Task Score | 72.2222
Mitigation Plan | Bootstrap function pushed over to iterartion 3

## Iteration 3
Task | Score
Slides for PM Review | 1
Update SDs | 1
Bootstrap UI | 1
Bootstrap Logic | 1
Bootstrap JSON | 1
Prepare Testcase for delete data function | 1
Consolidate Class Diagrams | 1
Consolidate ER Diagrams | 1
Draw SD for login | 1
Draw SD for Smartphone Usage Heatmap | 1
Prepare Testcase for basic app usage | 1
Prepare testcase for CRUD Location data | 1
Prepare testcase for smartphone usage heatmap | 1
Prepare testcase for login | 1
Login Logic | 1
Login UI | 1
Login JSON | 1
Delete Location UI | 1
Delete Location Logic | 1
Delete Location JSON | 1
Test Basic App Usage | 0
Test Delete Location | 0
Test Login | 1
SmartPhone Usage Heatmap UI | 1
SmartPhone Usage Heatmap Logic | 1
SmartPhone Usage Heatmap JSON | 1
PM Review | 1
Basic App Report Logic | 0
Basic App Report JSON | 0
Basic App Report UI | 0
Test Bootstrap | 1
Debug Heatmap | 1
Debug Login | 1
Debug Delete Location | 0
Debug Bootstrap | 0
Integrate functions | 1
Deploy to OpenShift | 1
Debug after deployment | 1
Regression Testing | 1
Peer Sharing | 1
PM Handover | 1
Update next Iteration | 1
Total Task Done | 35
Total number of Task | 42
Task Score | 83.3333
Mitigation Plan | 1) basic app (logic,UI,JSON,Testing) 2)Test & Debug Delete Location 3)Debug Bootstrap Pass all this to Next Iter

## Iteration 4
Task | Score
Test Basic App Usage (Openshift) | 1
Test Delete Location (Openshift) | 1
Basic App Report Function1 | 1
Basic App Report Function2 | 1
Basic App Report Function3 | 1
Debug Delete Location (Openshift) | 1
Debug Bootstrap (Openshift) | 1
Preparation of Material for supervisor Meeting | 1
Preparation of slides for Supervisor Meeting (Week 9) | 1
Update Bug Metrics | 1
Bootstrap Diagram | 1
Building of Test Cases Top-K | 1
Building of Test Cases (Smartphone Overuse Report) | 1
Building of Test Cases (Social Activeness) | 1
Building of Test Cases (Basic App) | 1
Develop Top-K students Most Apps usage (App Cat) | 1
Develop Top-K schools Most Apps usage (App Cat) | 1
Update Diagrams | 1
Social Activeness Report Logic | 0 | SW
Social Activeness Report UI | 0 | SW
Social Activeness Report JSON | 0 | SW
Friday Meeting | 1
Friday Meeting (PM handover) | 1
Pre-Supervisor Meeting | 1
Supervisor Meeting | 1
Smartphone overuse report Logic | 1
Smartphone overuse report UI | 1
Smartphone overuse report JSON | 1
Test TOP-K | 0
Test Basic App Usage | 1
Test Smartphone Overuse Report | 1
Debug Top-K | 0
Debug Basic App Usage | 1
Debug Smartphone Overuse Report | 1
Deploy application to OpenShift (Overuse + Basic App) | 1
Deploy application to OpenShift (Top-K) | 1
Testing on OpenShift (Overuse) | 1
Testing on OpenShift (Basic App) | 1
Debugging Overuse | 0 | SW
Debugging Basic App | 0 | SW
Total Task Done | 33
Total number of Task | 40
Task Score | 82.5
Mitigation Plan

## Iteration 5
Task | Score
Building of additional Test Case for Top k | 1
Testing of Top k report | 1
Debugging of Top-K report | 1
Preparation of slides for Supervisor Meeting 3 | 1
Changes to Bootstrap (Location-Delete) (Additional Change in Requirement) | 1
Supervisor Meeting 3 | 1
Building New Test Cases for Bootstrap change of demographic field (Additional Change in Requirement) | 1
Building Test Cases for Social Activeness Function | 1
Building of new Test Cases for Basic Add based on (Additional Change in Rerquiremenr | 1
Changes to Bootstrap - Additional Demographics (CCA) (Additional Change in Requirement) | 1
Debugging of Heatmap | 1
Debugging of Overuse | 1
Internal Meeting | 1
Testing of Bootstrap - Delete Location Data (Additional Change in Requirement) | 1
SOCIAL ACTIVENESS FUNCTION | 1
Testing of Bootstrap additional Demographics (Additional Change in Requirement) | 1
Changes to Basic App Requirement (Additional Change in Requirement) | 1
Regressison Testing | 1
Debugging of Basic App- Based on New test Cases (Additional Change in Requirement) | 1
Debugging of BootStrap Change in Demographics - Based on new Test Cases (Additional Change In Requirement) | 1
Debugging of BootStrap Delete Location - Based on new Test Cases (Additional Change In Requirement) | 1
Debugging of Social Activeness Report | 1
Deploy to OpenShift | 1
Overall Integration before deployment | 1
Testing of Bootstrap Basic App Function (Additional Change in Requirement) | 1
Testing of Social Activeness Function | 1
Update Metric and Apply Mitigration | 1
Revise Diagrams | 1
Code Sharing | 1
Internal Meeting | 1
PM Handover (Knowledge transfer on schedule, metrics, admin etc) | 1
Update next iteration schedule | 1
User Acceptance Test | 1
Total Task Done | 33
Total number of Task | 33
Task Score | 100
Mitigation Plan

## Iteration 6
Task | Score
Update and finalise ACTIVENESS SD | 0
Update and finalise BASIC APP SD | 1
Update and finalise Class Diagram | 1
Update and finalise HEATMAP SD | 1
Update and finalise Logical Diagram | 1
Update and finalise OVERUSE SD | 1
AddBatch DEBUGGING
Basic App DEBUGGING
Bootstrap DEBUG
Bootstrap JAVADOC
Final Presentation slides: Schedule, Metrics, Git usage, interesting experience
Overuse DEBUGGING
Topk DEBUGGING
Topk JAVADOCS
Update and finalise TOPK SDs
Activeness DEBUGGING
AddBatch JAVADOCS
Heatmap DEBUGGING
Overall UI DEBUGGING (fits requirements)
Delete Location DEBUGGING
Delete Location JAVADOCS
Entity (inc. DAO) JAVADOCS
Activeness JAVADOCS
AddBatch SD
Basic App JAVADOCS
Bootstrap SD
Delete Location SD
Heatmap JAVADOCS
Overuse JAVADOCS
Update and finalise DELETE LOCATION SD
Utility JAVADOCS
Integration, with thorough debugging, bug bust until 0 bugs (bugs metric) as end goal
Internal Meeting
Regression Testing
Deploy application to OpenShift
Final Submission
Total Task Done | 5
Total number of Task | 6
Task Score | 83.3333
Mitigation Plan