## Slide 1: Supervisor Meeting 3 (28/10/2015)
G3T3
SHU WEN
NABILAH
ZHIHUI
JEREMY
DARREN

## Slide 2: Meeting agenda
Progress for the past 2 weeks
Goals for the next 2 weeks
Problems that might threaten our progress
Task Metrics
Bug Metrics
PP Metrics

## Slide 3: Progress for the past 2 weeks

## Slide 4: Current status of functions as of the end of iteration 4
Functionality | Status as of Supervisor Meeting 2 | Current Status
1. Login | Testing on Openshift Done | Done testing on Open Shift
2. Bootstrap | JSON, Debugging | Working on changes of requirements
3. Basic App Usage Report | Function 1 done | All Functions done, working on changes of requirements
4. Top-k App Usage Report | Undone | Waiting to be tested on Open Shift
5. Smartphone Overuse Report | Undone | Debugging

## Slide 5: Current status of functions as of the end of iteration 4
Functionality | Status as of Supervisor Meeting 2 | Current Status
6. Deletion of location data | JSON, Debugging | Working on changes of requirements
7. Smartphone Usage Heatmap | Testing on Openshift Done | Found a bug, Debugging
8. Social Activeness Report | Undone | Working in progress

## Slide 6: SUB-Task(S) passed over from the last iteration
Debugging of Overuse Report
Social Activeness Function
Testing of Top K Report
Build Additional Test cases for Top K Report
Debugging of Top K Report
Debugging of Basic App
Debugging of Heatmap
Total Number of sub task(s) passed over from Iteration 4 to 5 :
7

## Slide 7: Additional Task(S) from change of requirement
Changes to Bootstrap function
Changes to Basic App function
Changes to Location delete function
Total Number of task(s)
from the change of requirements:
3
Notes:   Each task have 4 subtask
  Logic
  Building of New Test Cases
  Testing
  Debugging

## Slide 8: goals for the next 2 weeks

## Slide 9: expected status of functions
Functionality | Expected Status 2 weeks from now
1. Login | Done testing on Open Shift
2. Bootstrap | Done testing on Open Shift
3. Basic App Usage Report | Done testing on Open Shift
4. Top-k App Usage Report | Done testing on Open Shift
5. Smartphone Overuse Report | Done testing on Open Shift
6. Deletion of location data | Done testing on Open Shift
7. Smartphone Usage Heatmap | Done testing on Open Shift
8. Social Activeness Report | Done testing on Open Shift

## Slide 10: Critical path- iteration 5
Debug top k report (2 Days)
Changes to bootstrap Requirements- Delete Location
(2 Days)
Changes to bootstrap Requirements – CCA (2 Days)
Debug Heatmap (1 Days)
Debug Overuse Report (2 Day)
Continuing of Social Activeness Function(3 Days)
Changes to basic app requirement (2 Days)
Debugging of Bootstrap (1 day)
Debugging of Bootstrap – Location Delete (1day)
Debugging of Basic App (1 day)
Debugging of Social Activeness (1day)
Integrate and Regression Testing (1 Day)
End
Start
Diagrams (1 day)
1 day buffer
Notes: 12 days before submission for UAT, 11 days left
10 days(PAIR 2) vs 9 days(PAIR 1)
Top is critical path
9 is passed from previous iteration
1 from filed bugs(heat map)
1 is from mine – debug social activeness

## Slide 11: ACTIONS TAKEN
Additional 7 sub task would be brought over to iteration 5 from iteration 4.
Based on the Critical Path, we will be using up the full 1-week buffer before UAT for iteration 5 on these 7 tasks plus the additional requirements.
Because of this, we will not be brainstorming new Test Cases for UAT. The brainstorming of new Test Cases would be done in iteration 6 after UAT together with the needed changes.
We would not drop any functionalities.

## Slide 12: TASK METRICS

## Slide 13: Task Metrics
Current Iteration
75%
Overall Iteration
81.7 %
Task done/Total Task : [3/4]
(As of 27 Oct, 8pm)
Status : ON TIME
Task done/Total Task : [76/93]
(As of Iteration 1-5 + new Requirements)
Status : DELAYED
By 1 week

## Slide 14: BUG METRICS

## Slide 15: Bug Metrix - Iteration 5
Number of bugs at the start of iteration
        7
Bug Matrix as of yesterday(27/10/2012 8PM)
8
Notes: Bug now =7

## Slide 16: BUGS METRIX - Action taken
Bug | Action Taken
Bootstrap unable to load overly big data files. (v3,5,6) | We will settle this bug together with the debugging of Bootstrap additional requirement as it is currently not a critical bug now and would not affect the testing of other functions.
Unable to display correct result for overuse Report | We have scheduled for this bug to be fixed during the “debugging of overuse report” session as this is not a critical bug to other functions.
Top K’s bug | Still debugging

## Slide 17: PP METRICS

## Slide 18: HOURS PER MEMBER- Current
Chart: 
| Shuwen | Nabilah | Jeremy | Darren | Zhi Hui
Hours | 56.25 | 48.2 | 48.01 | 37.28 | 37.94

## Slide 19: Estimated HOURS PER MEMBER after iteration 5
Chart: 
| Shuwen | Nabilah | Jeremy | Darren | Zhi Hui
Hours | 56.25 | 63.2 | 62.01 | 61.28 | 61.94

## Slide 20
Thank you!