## Metrics
Issue | Function | Severity | Raw Score | Final Score | Description | Closed | Severity
1 | Bootstrap | C | 10 | 0 | test | Y | Low | L | 1
2 | Heatmap | L | 1 | 0 | semanticplacein json output not sorted | Y | High | H | 5
3 | Jsons | L | 1 | 0 | Jsons ordering unable to suit to wiki's requirements | Y | Critical | C | 10
4 | Bootstrap | L | 1 | 1 | Bootstrap is unable to insert special characters | N
5 | UI - Links | H | 5 | 0 | Broken links | Y | Total impact score: | 11 | <--- PM NOTE!!!!
6 | OpenShift-Bootstrap | H | 5 | 5 | appusage table and locationusage table not found; causes system to crash when initializing bootstrap. table name is caps Sensitive. need to rename in IDE. | N
7 | OpenShift-Heatmap | H | 5 | 0 | System crashes when heatmap request was sent. Possibly table name (appusage and locationusage) needs to be renamed (case sensitive) | Y
8 | Smartphone usage heatmap (via UI) | H | 5 | 0 | Crashes when input is: 6/04/2015 13:00:00 B1 | Y
9 | OpenShift-Initial Bootstrap | H | 5 | 5 | Bad Gateway:The proxy server received an invalid response from an upstream server. System unable to load a big zip file. (Might need to increase session time.) | N

## Guidelines
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.