## Mitigation Metrics
Score(%) | Action
TM <= 50 | 1.Immediately, inform your supervisor about the slip within 24 hours.
2.Then use the same mitigation as the category 50 < TM <= 90 and seriously consider dropping tasks.
50 < TM <= 90 | 1.Re-estimate the tasks for the future iterations.
2.Deduct the number of days behind schedule from buffer days.
3.If there is no more buffer day, decide the functionalities to drop.
90 < TM <= 110 | Our estimates are fairly accurate, and we are roughly on track.
1.Add/Deduct the number of days behind schedule from buffer days.
2.If there is no more buffer day, decide the functionalities to drop
110 < TM <= 150 | Gross over-estimated the effort required.
1.Re-estimate the tasks for the future iterations.
2.Add the number of days gained to buffer days.
150 < TM | 1.Immediately, inform your supervisor about the slip within 24 hours.
2.Then use the same mitigation as the category 110 < TM <= 150

## Iteration 1
Task | Score
Draw domain diagram | 1
Come out with project schedule | 1
Draw use case diagram | 1
Draw SD for initial bootstrap | 1
Draw ER Diagram | 1
Conduct per sharing | 1
PM Handover | 1
Update next Iteration schedule | 1
Total Task Done | 8
Total number of Task | 8
Task Score | 100
Mitigation Plan | Go ahead with planned schedule without any changes to buffer timing.

## Iteration 2
Task | Score
Update Bootstrap SD | 1
Draw SD Basic App Usage Report | 1
Draw SD Bootstrap Location Data | 1
Draw SD Deleting Location Data | 1
Draw SD Smartphone Overuse Report | 1
Draw SD Top-K Report | 1
Task Metrics | 1
Test Plan | 1
Prepare supervisor meeting slides | 1
Update SDs | 1
Bootstrap Logic | 0
Bootstrap JSON | 0
Bootstrap UI | 0
Deploy to openshift | 0
Test Bootstrap | 0
Conduct Peer Sharing Session | 1
PM Handover | 1
Update next Iteration schedule | 1
Total Task Done | 13
Total number of Task | 18
Task Score | 72.2222
Mitigation Plan | Bootstrap function pushed over to iterartion 3

## Iteration 3
Task | Score
Slides for PM Review | 1
Update SDs | 1
Bootstrap UI | 1
Bootstrap Logic | 1
Bootstrap JSON | 1
Prepare Testcase for delete data function | 1
Consolidate Class Diagrams | 1
Consolidate ER Diagrams | 1
Draw SD for login | 1
Draw SD for Smartphone Usage Heatmap | 1
Prepare Testcase for basic app usage | 1
Prepare testcase for CRUD Location data | 1
Prepare testcase for smartphone usage heatmap | 1
Prepare testcase for login | 1
Login Logic | 1
Login UI | 1
Login JSON | 1
Delete Location UI | 1
Delete Location Logic | 1
Delete Location JSON | 1
Test Basic App Usage | 0
Test Delete Location | 0
Test Login | 1
SmartPhone Usage Heatmap UI | 1
SmartPhone Usage Heatmap Logic | 1
SmartPhone Usage Heatmap JSON | 1
PM Review | 1
Basic App Report Logic | 0
Basic App Report JSON | 0
Basic App Report UI | 0
Test Bootstrap | 1
Debug Heatmap | 1
Debug Login | 1
Debug Delete Location | 0
Debug Bootstrap | 0
Integrate functions | 1
Deploy to OpenShift | 1
Debug after deployment | 1
Regression Testing | 1
Peer Sharing | 1
PM Handover | 1
Update next Iteration | 1
Total Task Done | 35
Total number of Task | 42
Task Score | 83.3333
Mitigation Plan | 1) Pass basic app (logic,UI,JSON,Testing) 2)Test & Debug Delete Location 3)Debug Bootstrap

## Iteration 4
Task | Score
Test case for Smartphone usage heatmap | 0
Testcase top-K | 0
Top-K Usage Report Logic | 0
Top-K Usage Report UI | 0
Top-K Usage Report JSON | 0
Update Diagrams | 0
Social Activeness Report Logic | 0
Social Activeness Report UI | 0
Social Activeness Report JSON | 0
Supervisor Meeting | 0
Smartphone overuse report Logic | 0
Smartphone overuse report UI | 0
Smartphone overuse report JSON | 0
Test Smartphone Usage Heatmap | 0
Test TOP-K | 0
Test case for Smartphone overuse report | 0
Debug Smartphone Usage Heatmap | 0
Debug Top-K | 0
Deploy to openshift | 0
Integrate functions | 0
Test on Openshift | 0
Debug on openshift | 0
Total Task Done | 0
Total number of Task | 22
Task Score | 0
Mitigation Plan

## Iteration 5
Task | Score
Test smartphone overuse report | 0
Debug smartphone overuse report | 0
Slides for supervisor meeting | 0
New testcases | 0
Test all functions with new testcases | 0
Debug based on nes test cases | 0
PM Handover | 0
Update Next iteration | 0
Total Task Done | 0
Total number of Task | 8
Task Score | 0
Mitigation Plan

## Iteration 6
Task | Score
Match final submission with requirements | 0
Seek loopholes in test cases | 0
Debugging | 0
Deploy to openshift | 0
Final presentation | 0
Total Task Done | 0
Total number of Task | 5
Task Score | 0
Mitigation Plan