## TestPlan
TEST Plan
Who are responsible for it? | PM of the iteration
When to do it? Frequency etc | Every Thursday after functions completed
Test Setup (People / Computers etc) | PM with own laptop
When to fix bugs? | Friday and over the weekends
Fix the bugs in pairs | Yes

## Bootstrap
TEST CASES
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | BootStrap | Validate that zip file with the correct file names,file type, number of files, input can be bootstrapped successfully. | File: bs-test-1.zip | Put the zip file into input field. Submit. | Bootstrap success. All bootstrap details are correctly displayed in the database. | Values printed as expected | Pass
2 | BootStrap | Error messages from validation in demographics.csv (based on mac-address,password,email,gender) are returned to admin correctly. | File: bs-test-2.zip | Put the zip file into input field. Submit. | Bootstrap success. However, 8 error messages are returned to admin. Row 3,4 will consist of mac-address error. Row 5,6,7 will consist of password error. Row 8,9 will consist of email error. Row 10 will consist of gender error. Rows 3,4,5,6,7,8,9,10 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass
3 | BootStrap | Error messages from validation in app-lookup.csv (based on app-id,app-category) are returned to admin correctly. | File: bs-test-3.zip | Put the zip file into input field. Submit. | Bootstrap success. However, 3 error messages are returned to admin. Row 3 ,5 will consist of app-id error. Row 10 will consist of app-category error. Rows 3,5,10 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass
4 | BootStrap | Error messages from validation in apps.csv (based on app-id,mac-address,timestamp) are returned to admin correctly. | File: bs-test-4.zip | Put the zip file into input field. Submit. | Bootstrap success. However, 6 error messages are returned to admin. Row 1,2 will consist of mac-address "invalid mac address" error. Row 3 will consist of mac-address "no matching mac address" error. Row 5 will consist of app-id error. Row 7 will consist of incorrect timestamp error. Row 10 will consist of a duplicated of row 9. Rows 1,2,3,5,7,9 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass
5 | BootStrap | Error messages from validation in location.csv (based on mac-address,location-id, timestamp) are returned to admin correctly. | File: bs-test-5.zip | Put the zip file into input field. Submit. | Bootstrap success. However, 6 error messages are returned to admin. Row 1 will consist of invalid location-id error. Row 5,6,20 will consist of invalid mac address error. Row 7 will consist of invalid timestamp error. Row 9 will consist of a duplicate of row 8. Rows 1,5,6,7,9,20 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass
6 | BootStrap | Error messages from validation in location-lookup.csv (based on location-id,semantic-place) are returned to admin correctly. | File: bs-test-6.zip | Put the zip file into input field. Submit. | Bootstrap success. However, 5 error messages are returned to admin. Row 1,2 will consist of invalid location id error. Row 8,9,10 will consist of invalid semantic place error. Rows 1,2,8,9,10 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass

## AddBatch
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | AddBatch | All files except demographics.csv should be throwing error messages for duplicates | File: ab-test-1.zip | Put the zip file into input field. Submit. | AddBatch success. However, error messages for app.csv and location.csv should be returned as all are duplicates. | Values printed as expected | Pass
2 | AddBatch | Error messages from validation in demographics.csv (based on mac-address,password,email,gender) are returned to admin correctly. | File: ab-test-2.zip | Put the zip file into input field. Submit. | AddBatch success. However, 8 error messages are returned to admin. Row 3,4 will consist of mac-address error. Row 5,6,7 will consist of password error. Row 8,9 will consist of email error. Row 10 will consist of gender error. Rows 3,4,5,6,7,8,9,10 will not be displayed in the database. All other rows should be displayed correctly. | Values printed as expected | Pass
3 | AddBatch | Error messages from validation in app.csv (based on app-id,mac-address,timestamp) are returned to admin correctly. | File: ab-test-3.zip | Put the zip file into input field. Submit. | AddBatch success. However, 18 error messages are returned to admin. Rows 3, 4, 5 have invalid timestamp, Rows 3, 5, 9, 11, 15 have duplicate mac address, Row 14 has invalid appid, Row 16 has no matching appid, | Values printed as expected | Pass
4 | AddBatch | Error messages from validation in location.csv (based on mac-address,location-id, timestamp) are returned to admin correctly. | File ab-test-4.zip | Put the zip file into input field. Submit. | Addbatch Success. Rows 2, 5, 7, 22, 26 have invalid timestamp. Rows 5, 10, 16, 22, 27, 28 have invalid location. Rows 5, 11, 21, 24 and 25 as well as 29 and 31. Rows 13, 24, 28 and 32 have duplicate mac addresses, but not duplicate timestamp. Rows 3, 4, 8, 12, 17, 19, 20 and 30 are duplicates in the database while rows 6, 9, 13, 14, 15, 18, 23, 25, 32. | Values printed as expected | Pass
5 | AddBatch | No error messages should be thrown. All files have unique records except for demographics.csv (assumed unique) | File ab-test-5.zip | Put the zip file into input field. Submit. | Addbatch success, no error messages. | Values printed as expected | Pass

## Login
TEST CASES | [7 empty] | 2015-10-04
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | User Login | Validate that correct username and password allow successful login | email:<email_Id> (email part before the @ sign) password: <password> from demographics.csv | Enter email ID and password, click login | A homepage with all the functions a User can access | This is home page for student users! | Pass | pass
2 | User Login | User enter email address instead of email ID | email:Email address password: <password> from demographics.csv | Enter user's full email address with the correct password and click login | Error Message saying invalid username/password on the log in page. | invalid username/password | Pass | pass
3 | User Login | User enter invalid email Id | email: abcabc password: <password> from demographics.csv | Enter invalid email id with any password found in demographics.csv and click login | Error Message saying invalid username/password on the log in page. | invalid username/password | Pass | pass
4 | User Login | User enter invalid password | email:<email_Id> (email part before the @ sign) password: abcabc from demographics.csv | Enter valid email id with wrong password and click login | Error Message saying invalid username/password on the log in page. | invalid username/password | Pass | pass
5 | User Login | User clicks login without entering any email id or password |  | Just click on login button | Error Message saying field should not be empty | error msg:" pls fill out this fied | Pass | pass
6 | User Login | User only enter emailId | email:<email_Id> (email part before the @ sign) password: from demographics.csv | Enter a valid email id and click login | Error Message saying field should not be empty | error msg:" pls fill out this fied on username field | Pass | pass
7 | User Login | User only enter password | email: password:<password> from demographics.csv | Enter only a valid password and click login | Error Message saying field should not be empty | error msg:" pls fill out this fied on password field | Pass | pass
8 | Admin Login | Validate that correct admin username and password allow successful login | email:<username> password:<password> from admin login.csv | Enter username and password, click login | A homepage with all the functions an admin can access | This is home page for admin! | Pass | pass
9 | Admin Login | admin does not enter username and password |  | Just click login | Error Message saying field should not be empty | error msg:" pls fill out this fied | Pass | pass
10 | Admin Login | Admin only enter password | email: password:<password> from admin login.csv | Enter the password and click login | Error Message saying field should not be empty | error msg:" pls fill out this fied | Pass | pass
11 | Admin Login | Admin only enter username | email: username password: from admin login.csv | Enter the username and click login | Error Message saying field should not be empty | error msg:" pls fill out this fied | Pass | pass
12 | Admin Login | Admin enter wrong username | email: abcabc password: <password> from admin Login.csv | Enter the invalid username with password given and click login | Error Message saying invalid username/password on the log in page. | invalid username/password | Pass | pass
13 | Admin Login | Admin enter wrong password | email: <username> password: abcabc from admin Login.csv | Enter the invalid password with username given and click login | Error Message saying invalid username/password on the log in page. | invalid username/password | Pass | pass
14 | User Login | correct username and password but password in Caps on | email:<email_Id> (email part before the @ sign) password: <PASSWORD> from demographics.csv | Enter valid emailID and valid password but the password in Capital Letters | Error Message saying invalid username/password on the log in page. | unable to check as given password is numerical. | Fail | pass
15 | Admin Login | correct username and password but password in Caps on | email:Username password: <PASSWORD> from admin login .csv | Enter valid username and valid password but the password in Capital Letters | Error Message saying invalid username/password on the log in page. | unable to check as given password is numerical. | Fail | pass
16

## BasicApp
TEST CASES
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | Usage time category (data v1) | check for blank fields | no input | just click submit | Please fill out this fields | Please fill out this fields | Pass
2 |  | invalid timestamp | start date : 06/04/0000 end date: 06/04/0000 | 1. At top navbar, click Basic App Usage dropdown and select 'Basic App (with demographic) 2. put in all the input according to input column and click submit | error msg: please fill in correct timestamp | Intense Users count: 0 Intense Percent: 0% Normal Users count: 0 Normal Percent: 0% Mild Users count: 0 Mild Percent: 0% | Fail
3 |  | End date before start date and vice versa | start date : 07/04/2015 end date: 06/04/2015 | Input: start date : 07/04/2015 end date: 06/04/2015 | End date should be after Start date | Intense Users count: 0 Intense Percent: 0% Normal Users count: 0 Normal Percent: 0% Mild Users count: 0 Mild Percent: 0% | Fail
4 |  | correct result shown | start date : 06/04/2015 end date: 06/04/2015 | 1. At top navbar, click Basic App Usage dropdown and select 'Basic App (with demographic) 2. put in all the input according to input column and click submit | Intense Users count: 0 Intense Percent: 0% Normal Users count: 7 Normal Percent: 7% Mild Users count: 100 Mild Percent: 93% | Intense Users count: 0 Intense Percent: 0% Normal Users count: 7 Normal Percent: 7% Mild Users count: 100 Mild Percent: 93% | Pass
5 | Usage time category and demographics | check for blank fields | no input | 1. At top navbar, click Basic App Usage dropdown and select 'Basic App (with demographic) 2. click submit | Please fill out this fields | Please fill out this fields | Pass
6 |  | invalid timestamp | start date : 06/04/0001 end date: 06/04/0001 Filter: gender, school, year | 1. At top navbar, click Basic App Usage dropdown and select 'Basic App (with demographic) 2. click submit | error msg: please fill in correct timestamp | Intense Users count: 0 Intense Percent: 0% Normal Users count: 0 Normal Percent: 0% Mild Users count: 0 Mild Percent: 0% | Fail
7 |  | valid start and end time plus checked year,checked gender and checked school option | start date : 06/04/2015 end date: 06/04/2015 Filter: gender, school, year | 1. At top navbar, click Basic App Usage dropdown and select 'Basic App (with demographic) 2. click submit | 3 tables for each usage level. Users break down and categorised by gender then school and then year M,55,51% - business, 10, 18% --- 2011,1,10% -----intense,0,0% -----normal,0,0% -----mild,1,100% --- 2012,3,30% -----intense,0,0% -----normal,1,33% -----mild,2,67% --- 2013,0,0% --- 2014,2,20% --- 2015,4,40% - accountancy,3,5% --- 2011,0,0% --- 2012,1,33% --- 2013,2,67% --- 2014,0,0% --- 2015,0,0% F, 52, 49% - business,6,12% ---2011,1,17% -----intense,0,0% -----normal,0,0% -----mild,1,100% ---2012,2,33% -----intense,0,0% -----normal,1,50% -----mild,1,50% ---2013,0,0% ---2014,0,0% ---2015,3,50% - accountancy, 10, 19% ---2011,2,20% ---2012,1,10% ---2013,1,10% ---2014,4,40% ---2015,2,20% | 3 tables for each usage level. Users break down and categorised by gender then school and then year M,55,51% - business, 10, 18% --- 2011,1,10% -----intense,0,0% -----normal,0,0% -----mild,1,100% --- 2012,3,30% -----intense,0,0% -----normal,1,33% -----mild,2,67% --- 2013,0,0% --- 2014,2,20% --- 2015,4,40% - accountancy,3,5% --- 2011,0,0% --- 2012,1,33% --- 2013,2,67% --- 2014,0,0% --- 2015,0,0% F, 52, 49% - business,6,12% ---2011,1,17% -----intense,0,0% -----normal,0,0% -----mild,1,100% ---2012,2,33% -----intense,0,0% -----normal,1,50% -----mild,1,50% ---2013,0,0% ---2014,0,0% ---2015,3,50% - accountancy, 10, 19% ---2011,2,20% ---2012,1,10% ---2013,1,10% ---2014,4,40% ---2015,2,20% | Pass
8 |  | valid start and end time plus select gender, school option | start date : 06/04/2015 end date: 06/04/2015 Filter: gender, school | 1. At top navbar, click Basic App Usage dropdown and select 'Basic App (with demographic) 2. click submit | 2 tables for each usage level. Users break down and categorised by gender then school M,55,51% - business, 10, 18% ---intense,0,0% ---normal,1,10% ---mild,9,90% - accountancy,3,5% ---intense,0,0% ---normal,0,0% ---mild,3,100% F, 52, 49% - business,6,12% ---intense,0,0% ---normal,1,17% ---mild,5,83% - accountancy, 10, 19% ---intense,0,0% ---normal,0,0% ---mild,10,100% | 2 tables for each usage level. Users break down and categorised by gender then school M,55,51% - business, 10, 18% ---intense,0,0% ---normal,1,10% ---mild,9,90% - accountancy,3,5% ---intense,0,0% ---normal,0,0% ---mild,3,100% F, 52, 49% - business,6,12% ---intense,0,0% ---normal,1,17% ---mild,5,83% - accountancy, 10, 19% ---intense,0,0% ---normal,0,0% ---mild,10,100% | Pass
9 |  | valid start and end time plus checked gender | valid start and end time plus checked gender option | 1. At top navbar, click Basic App Usage dropdown and select 'Basic App (with demographic) 2. click submit | 1 tables for each usage level. Users break down and categorised by gender then school M,55,51% ---intense,0,0% ---normal,6,11% ---mild,49,89% F, 52, 49% ---intense,0,0% ---normal,1,2% ---mild,51,98% | 1 tables for each usage level. Users break down and categorised by gender then school M,55,51% ---intense,0,0% ---normal,6,11% ---mild,49,89% F, 52, 49% ---intense,0,0% ---normal,1,2% ---mild,51,98% | Pass
10 | App category | check for blank fields | no input | just click submit | Please fill out this fields | Please fill out this fields | Pass
11 |  | invalid timestamp | start date : 06/04/0000 end date: 06/04/0000 | 1. At top navbar, click Basic App Usage dropdown and select 'App Category' 2. put in all the input according to input column and click submit | Invalid Date. Please select your desired date again | Invalid Date. Please select your desired date again | Pass
12 |  | correct result shown | start date : 06/04/2015 end date: 06/04/2015 | 1. At top navbar, click Basic App Usage dropdown and select 'App Category' 2. put in all the input according to input column and click submit | Books,3437,2% Education,527,0% Entertainment,3701,2% Fitness,0,0% Games,2674,2% Information,2861,2% Library,0,0% Local,1206,1% Others,70712,46% Social,67113,43% Tools,2530,2% | Books,3437,2% Education,527,0% Entertainment,3701,2% Fitness,0,0% Games,2674,2% Information,2861,2% Library,0,0% Local,1206,1% Others,70712,46% Social,67113,43% Tools,2530,2% | Pass
13 | App usage time | check for blank fields | no input | just click submit | Please fill out this fields | Please fill out this fields | Pass
14 |  | invalid timestamp | start date : 06/04/0001 end date: 06/04/0001 Filter: gender, school, year | 1. At top navbar, click Basic App Usage dropdown and select 'Diurnal Report' 2. put in all the input according to input column and click submit | error msg: please fill in correct timestamp | 00.00-01.00,0 01.00-02.00,0 02.00-03.00,0 03.00-04.00,0 04.00-05.00,0 05.00-06.00,0 06.00-07.00,0 07.00-08.00,0 08.00-09.00,0 09.00-10.00,0 10.00-11.00,0 11.00-12.00,0 12.00-13.00,0 13.00-14.00,0 14.00-15.00,0 15.00-16.00,0 16.00-17.00,0 17.00-18.00,0 18.00-19.00,0 19.00-20.00,0 20.00-21.00,0 21.00-22.00,0 22.00-23.00,0 23.00-00.00,0 | Fail
15 |  | correct result shown | start date : 06/04/2015 end date: 06/04/2015 Filter: gender=NA, school=NA, year=NA | 1. At top navbar, click Basic App Usage dropdown and select 'Diurnal Report' 2. put in all the input according to input column and click submit | 00.00-01.00,0 01.00-02.00,0 02.00-03.00,0 03.00-04.00,0 04.00-05.00,0 05.00-06.00,0 06.00-07.00,0 07.00-08.00,0 08.00-09.00,0 09.00-10.00,0 10.00-11.00,0 11.00-12.00,0 12.00-13.00,0 13.00-14.00,523 14.00-15.00,506 15.00-16.00,408 16.00-17.00,0 17.00-18.00,0 18.00-19.00,0 19.00-20.00,0 20.00-21.00,0 21.00-22.00,0 22.00-23.00,0 23.00-00.00,0 | 00.00-01.00,0 01.00-02.00,0 02.00-03.00,0 03.00-04.00,0 04.00-05.00,0 05.00-06.00,0 06.00-07.00,0 07.00-08.00,0 08.00-09.00,0 09.00-10.00,0 10.00-11.00,0 11.00-12.00,0 12.00-13.00,0 13.00-14.00,523 14.00-15.00,506 15.00-16.00,408 16.00-17.00,0 17.00-18.00,0 18.00-19.00,0 19.00-20.00,0 20.00-21.00,0 21.00-22.00,0 22.00-23.00,0 23.00-00.00,0 | Pass
16 |  | correct result shown | start date : 06/04/2015 end date: 06/04/2015 Filter: gender=M, school=economics, year=NA | 1. At top navbar, click Basic App Usage dropdown and select 'Diurnal Report' 2. put in all the input according to input column and click submit | 00.00-01.00,0 01.00-02.00,0 02.00-03.00,0 03.00-04.00,0 04.00-05.00,0 05.00-06.00,0 06.00-07.00,0 07.00-08.00,0 08.00-09.00,0 09.00-10.00,0 10.00-11.00,0 11.00-12.00,0 12.00-13.00,0 13.00-14.00,345 14.00-15.00,512 15.00-16.00,383 16.00-17.00,0 17.00-18.00,0 18.00-19.00,0 19.00-20.00,0 20.00-21.00,0 21.00-22.00,0 22.00-23.00,0 23.00-00.00,0 | 00.00-01.00,0 01.00-02.00,0 02.00-03.00,0 03.00-04.00,0 04.00-05.00,0 05.00-06.00,0 06.00-07.00,0 07.00-08.00,0 08.00-09.00,0 09.00-10.00,0 10.00-11.00,0 11.00-12.00,0 12.00-13.00,0 13.00-14.00,345 14.00-15.00,512 15.00-16.00,383 16.00-17.00,0 17.00-18.00,0 18.00-19.00,0 19.00-20.00,0 20.00-21.00,0 21.00-22.00,0 22.00-23.00,0 23.00-00.00,0 | Pass

## DeleteLocation
TEST CASES
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | upload the csv file and delete from location-delete.csv | Loop through the records in the csv and delete them from location.csv if they exist in the location.csv | location-delete.csv | at the delete data page, upload location-delete.csv | message: 16 location fies deleted .shown on the delete homepage
2 | upload the csv file and delete from location-delete.csv | Loop through the records in the csv and delete them from location.csv if they exist in the location.csv | location-delete_mixture.csv | at the delete data page, upload location-delete_mixture.csv | Message: 16 files deletd and 5 records not found. shown on the delete homepage
3 | Delete from web UI | admin will enter mac address, start date and end date. And the records that matches the input will be deleted | location-delete.csv
4
5
6
7
8
9
10

## SmartPhoneUsageHeatmap
TEST CASES
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | check for blank fields | no input | just click submit |  | error msg: please fill in all the fields
2 | valid start and end time | start time and end time in the right format | start time and end time | enter start and and time and click submit | A report with the overusae inex value together with the status set to either OVERUSE,NORMAL,TO_BE_CAUTIOUS
3
4
5
6
7
8
9
10

## Overuse
Test Cases **(FOR THESE TESTS, PLEASE USE sean.tan.2011@business.smu.edu.sg, asdf0000)
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | Smartphone Overuse | check for blank fields | no input | just click submit | Please fill out this fields | Please fill out this fields | Pass
2 | Smartphone Overuse | invalid timestamp | start date : 06/04/0000 end date: 06/04/0000 | Input: start date : 06/04/0000 end date: 06/04/0000 | Value must be 01/01/1970 or later | Value must be 01/01/1970 or later | Pass
3 | Smartphone Overuse | End date before start date and vice versa | start date : 07/04/2015 end date: 06/04/2015 | Input: start date : 07/04/2015 end date: 06/04/2015 | End date should be after Start date | Overuse results: Normal Usage results: Light,0 Gaming: Light,0 Access: Light ,0 | Fail
4 | Smartphone Overuse | correct result shown | start date : 06/04/2015 end date: 06/04/2015 | Using bs-test-1, enter inputs start date : 06/04/2015 end date: 06/04/2015 | Overall: Normal Smartphone: Light Gaming: Light Access: Light | Overall: Normal Smartphone: Light,0 Gaming: Light,0 Access: Light,0 | Pass
5 | Smartphone Overuse | Checks for overuse Checks whether the functions returns as an overuse (1 day) Tests if it is indeed calculations that 120s returns 120s and 121s returns 10s First to handle more than one static timing User starts to shift app (Meaning not just 1 static app) | start date : 06/04/2015 end date: 06/04/2015 | Using overuse-test-1 to bootstrap, enter inputs start date : 06/04/2015 end date: 06/04/2015 | Overall: Overuse Smartphone: Severe Gaming: Moderate Access: Light | Overuse results: Overusing Usage results: Light,5 Gaming: Moderate,1 Access: Severe,37056 | Fail
6 | Smartphone Overuse | Checks for overuse Checks whether the functions returns as an overuse (4 days) Tests if can handle over more than 1 day. Gaming will vary across the 4 days, along the borderline. User doesn't use the same app in chunks | start date : 06/04/2015 end date: 09/04/2015 | Using overuse-test-2 to bootstrap, enter inputs start date : 06/04/2015 end date: 09/04/2015 | Overall: Overuse Smartphone: Light Gaming: Severe Access: Light | Overuse results: Overusing Usage results: Light,2 Gaming: Severe,11 Access: Severe,7140 | Fail
7 | Smartphone Overuse | Checks for overuse Checks whether the functions returns as an overuse (3 days) Tests if gaming can separate between 3 appids and get moderate. Across more than 1 day, access will be close to the borderline | start date : 06/04/2015 end date: 08/04/2015 | Using overuse-test-3 to bootstrap, enter inputs start date : 06/04/2015 end date: 08/04/2015 | Overall: Overuse Smartphone: Light Gaming: Moderate Access: Severe | Blank screen | Fail
8 | Smartphone Overuse | Checks for overuse Checks whether the functions returns as an overuse (1 day) Overloads hours for access, tests whether can give the same result for all severe Tests whether it takes each hour into account | start date : 06/04/2015 end date: 06/04/2015 | Using overuse-test-4 to bootstrap, enter inputs start date : 06/04/2015 end date: 06/04/2015 | Overall: Overuse Smartphone: Severe Gaming: Severe Access: Severe | Overuse results: Overusing Usage results: Light,1 Gaming: Severe,4 Access: Severe,12432 | Fail

## Top-k
Test Cases **(FOR THESE TESTS, PLEASE USE sean.tan.2011@business.smu.edu.sg, asdf0000)
| S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
| 1 | Check for blank fields | Validates whether there is an entry | just click submit | Enter nothing | Error Message: Please fill in blanks
Top-k most used apps (given a school) | 2 | Check for date positions | Validates whether the start date is after the end date | Click submit | Enter a start date after the end date. | Error Message: End date is after start date
| 3 | Check for valid dates | Validates whether the start date can be before 1970 | Click submit | Enter 01/01/1970. | UI should NOT even let it pass
| 4 | Check for K value | Validates if the K value is only between 1 - 10. Checks if the K value is normally 3 | Click submit | Enter K value = 0 and another time > 11 | UI should NOT even let it pass, saying invalid K
| 5 | Check for forced entries | Validates if the K value is only between 1 - 10. Checks if the K value is normally 3 | Force a hyperlink with "?k=" as servlet still takes get | Enter into the hyperlink the values as stated | Should bring back to the home page and print error
| 6 | Check for end of the day | Validates whether the amount calculated into the program matches up to the end date | Bootstrap data v1.zip. | Enter start date as 01/01/2014 and end date 01/01/2016 and k as 10. Click Submit
| 7 | Check for printing consistency | Validates whether the printing is valid | Bootstrap data v1.zip.
8